## EpiSync
Vision Statement | Develop program that works across the entire pubic data ecosystem with integration to NBS system. Reduce burden on STLTs, capture standard & local data elements, shift mapping from stlts to CDC, and continuously perform reconciliation.
Goals | 1. Support the Generic v2 MMG in states that do not have the ability to send HL7. September 2023. 2. Support the DVH in pilot states, including the DVH MMG and STLT local questions. After Septemeber 2023. 3. EpiSync ships as a NBS 7.X feature. 2023.
Deliverables | 1. Feed and Dictionary standards for everyone in the ecosystem 2. EpiSync feeds publishing tool for NBS 6.0 and other ISS - (Integrated Surverllance Systems) deployments. The users can set up a feed, add a dictionary, and upload CSVs. This would have a UX to build an EpiSync dictionary and how it maps to MMG standards and local standards. 3. EpiSync Publish component to be built into NBS 7.0. 4. Validate component for DEX and NBS 7.0. 5. Possibly a mapping component for MVPS.
PO | Rick Hawes
D | Initiatives | 12 Month | Initiatives | TBD | Initiatives
Questions:
1. Define “Feed Standard”
2. Define “Publishing Tool”
3. Define “Publish Component”
4. Define “Validate component for DEX”

## Objective Details
Name of Deliverable Group | Team to deliver | Epic | Needs for Generic Goal | Needs for Viral Hepititcs Goal | Needs for NBS Goal
Standards | EpiSync | Produce standard data dictionaries | MMG generic data dictionary built by hand | Episync Data Create tool to handle the large number of elements in DVH and other MMGs | MMG AT integration, MMG AT publishing data dictionaries to an EpiSync Folder
Standards | EpiSync | Standard documents | Specification docs | Same | Same
Publish Tool | EpiSync | Publish component | Yes, run by the tool | Same | Yes, but run by export process
Publish Tool | EpiSync | Validate component | Yes, run by the tool | Same | Yes, but by NBS export process
Publish Tool | EpiSync | UX to create a data disctionary and map local data elements | Map column names only | Capture none standard questions and valuesets | Yes, but built into NBS question bank
Publish Tool | EpiSync
Publish Tool | EpiSync | CSV upload with validation | Yes | Yes
Publish Tool | EpiSync or MVPS team | … hosting and authentication | Yes | Yes
Mapping component | EpiSync or MVPS team | Mappings and mapping component | No | Yes, | No
NNDSS Reads EpiSync | DEX | EpiSync blob stores for STLTs | Yes | Same | Same
NNDSS Reads EpiSync | DEX | EpiSync blobs are validated using EpiSync validation tool | Yes | Same | Same
NNDSS Reads EpiSync | MVPS | MVPS puts EpiSync data into consolidated tables | Yes, but only generic v2 | MVPS has the ability to handle arbritary questions | Same
Program | EpiSync | CI/CD
Program | EpiSync | …

## Activities & Milestones
Activities | Tasks
Possibly a mapping component for MVPS. | Rick to introduce Peter to Andrew to schedule a meeting with MVPS team
Get MMGAT to publish EpiSync Data Dictionaries | Rick to introduce Peter to Andrew to schedule a meeting with MMGAT team
Events (Milestones)
Council for State & Territorial (CST)
Architectural Review Council
Data Modernization Initiative Governance Council (DMI)